## Audience-Completed
User Action | Endpoints | Method | Request Body | Response | status
List | /audiences/search/all | GET |  |  | Completed
list active audience | /audiences/search/all/active | GET |  |  | Completed
details | /audiences/search/details/:id | GET |  |  | Completed
unique | /audiences/isUnique/:name/:id | GET |  |  | Completed
save | /audiences/save | POST | id with 0 value |  | Completed
update | /audiences/update | PUT | id with value |  | Completed
update active flag | /audiences/update | PUT | id with value and changed active value |  | Completed
delete | /audiences/update | PUT | DELETE FLAG AS 1 |  | Completed
list categories | /categories/search/all | GET |  |  | Completed
list class | /classes/search/all | GET |  |  | Completed
list section | /sections/search/all | GET |  |  | Completed
UI
One minor issue of selection is still remaining which randomly appear

## Guardian
User Action | Endpoints | Method | Request Body | Response | Backend Status | status
List | /guardian/search/all | GET |  |  | Completed | Completed
details | /guardian/search/details/:id | GET |  |  | Completed | completed
unique | /guardian/isUnique/:cnic/:id | GET |  |  | Completed | TODO | not working properly
uniqueEmail | /guardian/search/details/email/unique/:email/:id | GET |  |  | Completed | TODO | not working properly
save | /guardian/save | POST | id with 0 value |  | Completed | Completed
update | /guardian/update | PUT | id with value |  | Completed | Completed
delete | /audiences/update | PUT | DELETE FLAG AS 1 |  | Completed | Completed
list area | /areas/search/all | GET |  |  | Completed | Completed
list profession | /profession/search/all | GET |  |  | Completed | Completed
UI issues
dropdown is not automatically selected in edit
view showing object for dropdown values

## Notification
User Action | Endpoints | Method | Request Body | Response | status
List | /notifications/search/all | GET |  |  | Completed
list active audience | /audiences/search/all/active | GET |  |  | Completed
details | /notifications/search/details/:id | GET |  |  | Completed
save | /notifications/send | POST |  |  | Completed
delete | /notifications/delete/:id | DELETE | DELETED AS 1 |  | NOT WORKING

## Notification Detail
User Action | Endpoints | Method | Request Body | Response | Status
ListUserNotification | /notifications/search/all | GET |  |  | TODO

## Student
User Action | Endpoints | Method | Request Body | Response | Backend Status | status
List | /students/search/all | GET |  |  | Completed | Completed
details | /students/search/details/:id | GET |  |  | Completed | completed
save | /students/save | POST | id with 0 value |  | Completed | completed
update | /students/update | PUT | id with value |  | Completed | completed
delete | /students/update | PUT | DELETE FLAG AS 1 |  | Completed | TODO
guardian detail by nic | /guardian/search/details/cnic/{nic} | GET |  |  | Completed | completed
list categories | /categories/search/all | GET |  |  | Completed | completed
list class | /classes/search/all | GET |  |  | Completed | completed
list section | /sections/search/all | GET |  |  | Completed | completed
list placeofbirth | /placeOfBirth/search/all | GET |  |  | Completed | Completed
list religion | /religion/search/all | GET |  |  | Completed | Completed
list nationality | /nationality/search/all | GET |  |  | Completed | Completed
list lastSchool | /lastschools/search/all | GET |  |  | Completed | Completed
list houses | /houses/search/all | GET |  |  | Completed | Completed
unique email | /students/search/details/email/unique/:email/:id | GET |  |  | Completed | TODO

## Employee
User Action | Endpoints | Method | Request Body | Response | Backend Status | status
List | /employee/search/all | GET |  |  | Completed | TODO
details | /employee/search/details/:id | GET |  |  | Completed | TODO
save | /employee/save | POST | id with 0 value |  | Completed | TODO
update | /employee/update | PUT | id with value |  | Completed | TODO
delete | /employee/update | PUT | DELETE FLAG AS 1 |  | Completed | TODO
list designation | /designation/search/all | GET |  |  | Completed | TODO
list qualification | /qualification/search/all | GET |  |  | Completed | TODO
list area | /areas/search/all | GET |  |  | Completed | Completed
unique email | /employee/search/details/email/unique/:email/:id | GET |  |  | Completed | TODO

## Create Session
User Action | Screen | Endpoints | Method | Request Body | Response | Backend Status | status
list examtitles | step 2
save examtitles | step 2
update examtitles | step 2
delete examtitles | step 2
list examtype | step 2
save examtype | step 2
update examtype | step 2
delete examtype | step 2
list sessioninfo | step 1
save sessioninfo | step 1
update sessioninfo | step 1
delete sessioninfo | step 1
list subject title | step 3
save subject title | step 3
update subjects title | step 3
delete subjects title | step 3
list session subject | step 3
update session subject | step 3
save session subject | step 3
delete session subject | step 3
list session exam | step 2
update session exam | step 2
delete session exam | step 2
save session exam | step 2
list session test info | step 4
add session test info | step 4
delete session test info | step 4
update session test info | step 4
execute session | Step 5

## Munawar TODO List
TASK FOR MUNAWAR
----------------
1) add deleted field in student table and change in search to make sure that deleted are not shown on screen
2) /student/update end point require
4) create new table with name designation. make it similar to qualification table. add teacher as one designation in it as well.
5) create delete field for employee
6) Following enpoint need to be created for employee
/employee/search/all
/employee/search/details/:id
/employee/save
/employee/update
/designation/search/all
/qualification/search/all
/guardian/isUnique/:cnic/:id
/guardian/search/details/email/unique/:email/:id
7) On Save of Guardian, send an email to guardian with the email address given during addition.
like wise on update, send an email to guardian
like wise on delete, send an email to guardian --> change end point as both endpoint are save for update and delete
8) add email field in guardian table.
9) add deleted field in student table
10) update, detail and delete of student is not working from backend have shared logs in email
11) add email field in student table
12) unique validation of student against email
13) Dashboard when data is not load fails. Please check email for details | FIXED
14) notifications/delete/:id return success but it doesn't delete base notification record |  | created: 09/10/2019
unique email and unique cnic of guardian is still not working properly, email sent |  | created: 09/10/2019
grno and regno is not automatically generated |  | created: 10/10/2019